USVI Evaluation Plan

Research Assistants

- Between 10-12 students total should be trained for the research team. This size allows for:

  - Flexibility: can more easily schedule people to collect data at different times of the day

  - Attrition: fewer worries about assistants dropping out over time

  - Inter-rater reliability: can calculate the level of agreement across team members

  - Accountability: assistants can work in pairs, keeping everyone more accountable

- Matching t-shirts should be provided

  - University of the Virgin Islands logo? VI Walkability Institute?

  - Lends legitimacy to their requests; may reduce discomfort in respondents; makes assistants feel like they’re part of a team; bright colors for safety of surveyors who are on the street.

- Incentives should be provided

  - Class credit? Research experience? Payment?

  - Will help to retain students for all stages of data collection

|  | Task | # and who | Position | Supplies |
| --- | --- | --- | --- | --- |
| Team Lead | Coordinate the students, troubleshoot issues, track data collection | 1 non-student (VI Walkability Inst.?) | Nearby where data is being collected, but out of sight | Extra copies of surveys and data collection tools |
| Surveyors | Administering intercept surveys | 2 students | a) A pair on one side of the street, or b) one person on each side | Paper copies of survey, visual aid for Likert scale questions, pencils, clipboards |
| Speed Readers | Collecting car speed information | 2 students (one to hold the radar gun, one to write down speed) | Parked near the signage area | Radar gun, data collection sheet (hardcopy or excel file) |
| Observers | Collecting drivers’ yielding behavior Could also take photos of crossing for future presentations | 1-2 students (if heavy traffic, could have one see if the first/any car stops and one to count the # of passing cars) | Parked where they can see the full crossing | Data collection sheets, pencils Camera for photos GoPro? |

- Data should be collected in 3 teams of 5-6 people, plus 1 Team Lead

Other supplies

- Digital counter for the pedestrian bridge

- Optional

  - Walkie-talkies so teams can communicate?

  - Go Pro to record footage to be coded later? Eliminates need for on-the-ground Observer team.

Timeline for Data Collection

1) Piloting Phase (Mid-January)

- The location of the demonstration project needs to be scouted by members of the USVI team prior to data being collected

- Questions that need answering:

  - How heavy is traffic in the area?

    - Is the proposed protocol feasible based on traffic?

  - How frequently do pedestrians try to cross at the site?

  - Where should the research assistants be positioned?

    - Is there a place to park cars nearby for the Speed Readers and the Observers?

    - Where should the Surveyors stand?

  - Is the data collection tool for driver yielding behavior feasible for one person, or do things move too fast?

  - Is it clear when a “trial” starts?

    - At which point do approaching pedestrians and oncoming cars constitute a trial?

  - What are the peak hours of traffic?

    - This is when data should be collected

  - Are the survey questions appropriate?

2) Training Phase (Late January)

- Training Session for Research Assistants

  - To meet, learn about the study and the different roles they can play, and practice gathering data in real time at the location

- Should only take a day

- Interrater reliability for the Observers can be assessed at this time

  - All Observers should collect the same data from the same trials.

    - Will need a sample of 20-30 trials to calculate interrater reliability.

  - Must know that the Observers are consistently seeing the same thing in order to trust the data from any one assistant.

3) Pre-test Phase (Early February)

- Aim for at least 100 trials and surveys (the more, the better!!)

- Data to be collected:

  - During peak hours, in no more than 3 hr. blocks of time

    - e.g. 10 AM-12 PM, 4-6 PM

      - except for pedestrian bridge counter, which can be left running

      - Weekdays? Weekends?

    - Should continue data collection until at least 100 trails/surveys collected

  - Only on fair weather days

    - The weather should be consistent

    - The Team Lead can decide to cancel data collection on rainy days

4) Post-test 1 Phase (Mid-Late February)

- After the demonstration project has been installed

  - If more than one month after the pre-test, consider a brief refresher training

- Data collection schedule should be identical to pre-test, with similar number of trials

5) Post-test 2 Phase (Late May-Early June)

- The follow-up; demonstration project should still be in place

- Brief refresher training for research assistants

- Data collection schedule should be identical to pre-test, with similar number of trials